## GanttChart
空气质量可视化系统实施计划 | [7 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com
| 项目开始日期 | 2023-03-09 |  |  | 显示周 |  | 1 | 第 1 周 | [6 empty] | 第 2 周 | [6 empty] | 第 3 周 | [6 empty] | 第 4 周 | [6 empty] | 第 5 周 | [6 empty] | 第 6 周 | [6 empty] | 第 7 周 | [6 empty] | 第 8 周
| 项目经理 | 许文杰 | [5 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24
 | time axis 2023-03-06 to 2023-04-30
WBS | 任务 | 任务负责人 | 开始日期 | 结束日期 | 天数 | %完成 | time axis 2023-03-06 to 2023-04-30
1 | [需求分析]
1.1 | 确定系统功能 | 许文杰 | 2023-03-09 | 2023-03-11 | 3 | 100%
1.2 | 确定系统技术框架 | 许文杰 | 2023-03-09 | 2023-03-11 | 3 | 100%
2 | [概要设计]
2.1 | 划分功能模块 | 许文杰 | 2023-03-12 | 2023-03-15 | 4 | 100%
2.2 | 定义各功能模块接口 | 许文杰 | 2023-03-12 | 2023-03-15 | 4 | 100%
2.3 | 数据库设计 | 许文杰 | 2023-03-14 | 2023-03-15 | 2 | 100%
3 | [课堂汇报准备]
3.1 | 制作项目实施计划与甘特图 | 许文杰，陆仟龙，赵睿睿 | 2023-03-16 | 2023-03-23 | 8 | 100%
3.2 | 开会讨论各自进度规划 | 许文杰，陆仟龙，赵睿睿 | 2023-03-23 | 2023-03-23 | 1 | 100%
3.3 | 课堂演讲准备与PPT制作 | 许文杰，陆仟龙，赵睿睿 | 2023-03-24 | 2023-03-30 | 7 | 100%
4 | [详细设计]
4.1 | 设计数据预处理方法 | 许文杰 | 2023-03-25 | 2023-03-30 | 6 | 100%
4.2 | 确定前后端接口请求与响应数据格式 | 许文杰 | 2023-03-31 | 2023-04-01 | 2 | 100%
4.3 | 设计后端各功能接口的具体实现内容 | 许文杰 | 2023-04-02 | 2023-04-04 | 3 | 100%
5 | [代码实现与测试]
5.1 | 编写前端整体页面和样式布局 | 陆仟龙，赵睿睿 | 2023-04-04 | 2023-04-15 | 12 | 100%
5.2 | 数据集逆地理编码 | 许文杰 | 2023-04-04 | 2023-04-11 | 8 | 100%
5.3 | 数据库创建与数据导入 | 许文杰 | 2023-04-12 | 2023-04-15 | 4 | 100%
5.4 | 编写中国地图各省的污染平均值接口 | 许文杰 | 2023-04-12 | 2023-04-16 | 5 | 100%
5.5 | 编写中国地图展示页面 | 陆仟龙，赵睿睿 | 2023-04-16 | 2023-04-20 | 5 | 100%
5.6 | 测试5.4和5.5前后端接口交互 | 许文杰，赵睿睿 | 2023-04-20 | 2023-04-21 | 2 | 100%
5.7 | 编写根据年份获取各个省的污染物平均值和根据省的名称获取城市污染数据接口 | 许文杰 | 2023-04-16 | 2023-04-19 | 4 | 100%
5.8 | 编写中国地图数据下钻功能 | 陆仟龙，赵睿睿 | 2023-04-20 | 2023-04-24 | 5 | 100%
5.9 | 测试5.7，5.8前后端接口交互 | 许文杰，赵睿睿 | 2023-04-25 | 2023-04-26 | 2 | 100%
5.10 | 编写获取近六年省份污染物平均值和获取目标年城市污染物平均值接口 | 许文杰 | 2023-04-20 | 2023-04-24 | 5 | 100%
5.11 | 编写根据省份和城市污染物可视化柱状图 | 陆仟龙，赵睿睿 | 2023-04-24 | 2023-04-27 | 4 | 100%
5.12 | 测试5.10，5.11前后端接口交互 | 许文杰，赵睿睿 | 2023-04-28 | 2023-04-29 | 2 | 100%
5.13 | 编写获取近六年全国的前十个省的污染物数据和获取近六年全国的污染物平均值接口 | 许文杰 | 2023-04-25 | 2023-04-29 | 5 | 100%
5.14 | 编写获取近六年全国的污染物动态排序柱状图 | 陆仟龙，赵睿睿 | 2023-04-30 | 2023-05-04 | 5 | 100%
5.15 | 测试5.13和5.14前后端接口交互 | 许文杰，赵睿睿 | 2023-05-04 | 2023-05-05 | 2 | 100%
5.16 | 编写获取近六年某省份的前十名城市污染物数据和污染物平均数据接口 | 许文杰 | 2023-05-07 | 2023-05-11 | 5 | 100%
5.17 | 编写获取近六年某省份的污染物饼图和折线图 | 陆仟龙，赵睿睿 | 2023-05-11 | 2023-05-15 | 5 | 100%
5.18 | 测试5.15，5.17前后端接口交互 | 许文杰，赵睿睿 | 2023-05-15 | 2023-05-16 | 2 | 100%
5.19 | 编写各市详细展示页面，包括日历图、散点图 | 陆仟龙，赵睿睿 | 2023-05-17 | 2023-05-21 | 5 | 100%
5.20 | 测试5.19前后端接口交互 | 赵睿睿 | 2023-05-21 | 2023-05-22 | 2 | 100%
6 | [项目验收] |  |  |  |  | 100%
6.1 | 检查系统各模块交互是否存在异常 | 许文杰，陆仟龙，赵睿睿 | 2023-05-23 | 2023-05-24 | 2 | 100%
7 | [课堂汇报准备] |  |  |  |  | 100%
7.1 | 制作演讲PPT与准备演讲 | 许文杰，陆仟龙，赵睿睿 | 2023-05-25 | 2023-05-31 | 7 | 100%

## Help
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
• Some of the labels include cell comments to provide extra information.
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• For each task, enter the Start Date and the duration of the task in Days. The End Date and Work Days columns are calculated using formulas.
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC